EDDIEfication SOP (Executive Version)
Productionizing an ML Use Case

# 1. Overview

EDDIEfication is the structured process of transforming a machine learning use case into a production-ready system on EDDIE. It ensures reliability, automation, governance, and scalability across Dev, Stage, and Prod environments.

# 2. Phases

Dev – Build, integrate, and stabilize

Stage – Validate and approve

Prod – Deploy and operationalize

# 3. Key Steps (Detailed Execution)

Steps 1–26: Development (code, data, infra, orchestration)

Steps 27–35: Stage validation (integration + CR approval)

Steps 36–41: Production deployment (go-live + monitoring)

# 4. Timeline / Gantt View

| Phase | Steps | Duration (Days) |
| --- | --- | --- |
| Dev | 1–26 | 100 |
| Stage | 27–35 | 25 |
| Prod | 36–41 | 18 |

1. What is EDDIEfication?

EDDIEfication is the complete process of converting a machine learning solution into a production-ready pipeline on the EDDIE platform.
It ensures code, data, infrastructure, permissions, and scheduling are all correctly configured so the system runs automatically and reliably.
This includes development setup, validation in staging, and final deployment in production.

2. End-to-End Flow

- Dev → Build + Integrate + Stabilize

- Stage → Validate + Approve

- Prod → Deploy + Operationalize

🔵 PHASE 1: DEV (Development & Testing)

Step 1: Refactor Code (Duration: 8 days)

What to do:

- Review entire codebase (scripts, notebooks, modules)

- Remove hardcoded paths, credentials, and local dependencies

- Modularize code into reusable functions

- Standardize naming conventions

Validation:

- Code runs independently without manual edits

- No local dependencies remain

Step 2: Onboard Use Case into EDDIE (3 days)

What to do:

- Register use case in EDDIE portal

- Provide metadata (use case name, owner, description)

- Map project to correct business domain

Validation:

- Use case visible in EDDIE dashboard

Step 3: Raise AD Access Requests (3 days)

What to do:

- Identify required AD groups (EDNA, EDDIE, MFT, etc.)

- Raise access request via internal tool

- Follow up with approvers

Validation:

- Access confirmed via login/test queries

Step 4: Test Pipeline in Workbench (3 days)

What to do:

- Execute pipeline manually

- Run all modules sequentially

- Check logs for failures

Validation:

- End-to-end pipeline runs successfully

Step 5: Setup EDNA Tollgate Ingestion (3 days)

What to do:

- Identify source data (rep-level data)

- Configure ingestion pipeline in EDNA

- Define schema and partitions

Validation:

- Data available in EDNA tables

Step 6: Raise EDNA Consumption Request (3 days)

What to do:

- Submit request for dataset consumption

- Specify downstream usage

Validation:

- Data accessible for pipeline

Step 7: Create MFT Ticket (3 days)

What to do:

- Raise request for file transfer setup

- Provide source, destination, frequency

Validation:

- MFT pipeline configured

Step 8: Perform MFT Testing (3 days)

What to do:

- Trigger file transfer

- Validate file arrival and format

Validation:

- Files correctly transferred

Step 9: Raise Change Request (CR) (3 days)

What to do:

- Document all data/system changes

- Submit CR for approval

Validation:

- CR approved

Step 10–11: Push Data to EDNA (Repeated) (3 days each)

What to do:

- Load sales rep data into EDNA

- Repeat load for validation consistency

Validation:

- Data correctly populated and verified

Step 12: Create Output Tables (3 days)

What to do:

- Define schema for outputs

- Create tables in EDNA-EDD-PR

Validation:

- Tables created and queryable

Step 13: Enable Dataset Consumption (3 days)

What to do:

- Create VW, VI2, D2 datasets

- Enable tollgate consumption

Validation:

- Empty datasets available

Step 14: Create VW Views (3 days)

What to do:

- Build views on D2 tables

- Standardize transformations

Validation:

- Views return correct data

Step 15: Provide Service Account Access (3 days)

What to do:

- Grant access to EDNA datasets

- Map service account permissions

Validation:

- Pipeline can access data without manual login

Step 16: Validate Access (3 days)

What to do:

- Test read/write permissions

- Execute sample queries

Validation:

- No permission errors

Step 17: Validate Modules (4 days)

What to do:

- Test each module independently

- Check outputs for correctness

Validation:

- All modules working correctly

Step 18: Update Config File (4 days)

What to do:

- Add environment variables

- Update dataset paths and parameters

Validation:

- Config loads without errors

Step 19: Dockerization (5 days)

What to do:

- Create Dockerfile

- Add requirements.txt

- Build container image

Validation:

- Container runs successfully

Step 20: Trigger Pipeline (4 days)

What to do:

- Execute pipeline using config

- Monitor logs

Validation:

- Successful execution

Step 21: Fix Issues (4 days)

What to do:

- Debug failures

- Fix code/config issues

Validation:

- No runtime errors

Step 22: Integrate with Vertex AI (4 days)

What to do:

- Connect pipeline to Vertex AI

- Configure job execution

Validation:

- Jobs executed successfully

Step 23: Push Code to GitHub (4 days)

What to do:

- Commit final code

- Create version tags

Validation:

- Repo updated

Step 24–25: Fix + Revalidate Integration (4 days each)

What to do:

- Fix issues

- Re-test integration

Validation:

- Stable pipeline

Step 26: Integrate Airflow DAG (4 days)

What to do:

- Create DAG

- Schedule pipeline

- Deploy to Airflow

Validation:

- Automated runs successful

🟡 PHASE 2: STAGE (Validation)

Step 27: Send Onboarding Email (4 days)

What to do:

- Inform EDDIE team for stage setup

Step 28: Coordinate with EDDIE Team (3 days)

What to do:

- Align timelines

- Resolve dependencies

Step 29: Provide Access (3 days)

What to do:

- Grant stage environment access

Step 30–32: Perform Stage Integration (3 days each)

What to do:

- Deploy pipeline in stage

- Validate all integrations (EDNA, MFT, Airflow)

Validation:

- End-to-end execution works

Step 33: Prepare CR Documents (3 days)

What to do:

- Compile documentation for approval

Step 34: Conduct CR Review (3 days)

What to do:

- Present to stakeholders

Step 35: Activate CR (3 days)

What to do:

- Get final approval

Validation:

- CR active

🔴 PHASE 3: PROD (Deployment)

Step 36: Send Onboarding Email (3 days)

What to do:

- Notify EDDIE team for production

Step 37: Coordinate with Team (3 days)

What to do:

- Final deployment planning

Step 38: Provide Access (3 days)

What to do:

- Configure production permissions

Step 39–41: Perform Production Integration (3 days each)

What to do:

- Deploy pipeline

- Enable live data ingestion

- Run first execution

Validation:

- Pipeline runs successfully

- Outputs correct

- System stable

✅ FINAL STEP: COMMUNICATION

Send Completion Email

Subject: EDDIEfication Successful – [Use Case Name]

Body:

- Dev, Stage, and Prod completed successfully

- Pipeline is live on EDDIE

- All integrations (EDNA, MFT, Airflow, Vertex AI) working

- Outputs validated

- Notes: [if any]